## Risk Register
Risk ID | Asset | Asset Type | Information / Value | Risk Statement | Threat Source | Relevant NIST Controls | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Treatment / Planned Controls | Risk Owner | Response | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Target Date | Status
RA-001 | Customer Data Store | Cloud database / analytics warehouse | Customer PII and account metadata | Unauthorized access or excessive privileges expose customer data | Identity compromise / privilege misuse | AC-2, AC-6, IA-2, AU-2/AU-12 | 4 | 5 | 20 | High | Implement least privilege, quarterly access review, MFA, privileged activity logging | Security / IAM | Reduce | 2 | 5 | 10 | Medium | 2026-11-15 | Open
RA-002 | Production API | Public-facing SaaS API | Customer data and application functionality | API abuse or exploitable authorization flaw enables unauthorized data access | External attacker | AC-3, AC-4, SC-7, SI-10, SA-11 | 4 | 5 | 20 | High | API authorization testing, WAF/rate limiting, secure SDLC testing, logging | Engineering | Reduce | 2 | 5 | 10 | Medium | 2026-12-01 | Open
RA-003 | Cloud IAM | Cloud identity and privileged roles | Administrative access | Compromised privileged account could alter infrastructure or access sensitive data | Credential theft / phishing | IA-2, IA-5, AC-6, AU-12 | 4 | 5 | 20 | High | Phishing-resistant MFA for admins, PAM/JIT access, access recertification, alerting | Security / IAM | Reduce | 2 | 5 | 10 | Medium | 2026-11-01 | Open
RA-004 | Backups | Production backup repository | Customer and operational data | Ransomware or accidental deletion compromises recoverability | Ransomware / admin error | CP-2, CP-6, CP-9, SC-28 | 3 | 5 | 15 | High | Immutable backups, separate credentials, restore tests, backup monitoring | Infrastructure | Reduce | 1 | 5 | 5 | Low | 2026-11-30 | Open
RA-005 | CI/CD Pipeline | Source control and deployment pipeline | Application source code and deployment credentials | Compromised pipeline introduces malicious code into production | Supply-chain compromise / stolen token | SA-10, SA-11, CM-3, AC-6, IA-5 | 3 | 5 | 15 | High | Branch protection, signed commits/artifacts, secret scanning, restricted runners, separation of duties | Engineering | Reduce | 2 | 5 | 10 | Medium | 2026-12-15 | Open
RA-006 | Employee Endpoints | Corporate laptops | Credentials and business information | Malware or lost device leads to credential theft or data exposure | Malware / loss or theft | CM-8, MP-4, SC-28, SI-3, AC-19 | 3 | 4 | 12 | Medium | EDR, full-disk encryption, MDM, screen lock, remote wipe, security awareness | IT / Security | Reduce | 1 | 4 | 4 | Low | 2026-11-15 | Open
RA-007 | Third-Party SaaS | Critical vendors processing company/customer data | Data and business operations | Vendor breach or service failure affects confidentiality or availability | Third-party compromise / outage | SR-3, SR-6, CA-3, SA-9 | 3 | 4 | 12 | Medium | Vendor due diligence, security clauses, annual reassessment, dependency inventory, exit plans | GRC / Procurement | Reduce | 2 | 4 | 8 | Medium | 2026-12-20 | Open
RA-008 | Logging Platform | Central security and application logs | Audit evidence and security telemetry | Insufficient logging or tampering reduces incident detection and audit evidence quality | Insider / attacker activity | AU-2, AU-6, AU-9, AU-12 | 3 | 4 | 12 | Medium | Centralized logging, restricted access, retention standard, alert coverage review, time synchronization | Security Operations | Reduce | 1 | 4 | 4 | Low | 2026-11-10 | Open
RA-009 | Security Awareness | Employees / contractors | Human access to systems and data | Successful phishing or social engineering results in credential compromise | Social engineering | AT-2, AT-3, IA-2 | 4 | 4 | 16 | High | Quarterly training, phishing simulations, targeted training for privileged users | GRC / People | Reduce | 2 | 4 | 8 | Medium | 2026-12-05 | Open
RA-010 | Incident Response | IR process, contacts and playbooks | Incident handling capability | Delayed or unclear response increases impact of a security event | Process gap / coordination failure | IR-2, IR-4, IR-6, CP-2 | 3 | 5 | 15 | High | Define severity matrix, playbooks, contact tree, tabletop exercise, lessons learned | Security / GRC | Reduce | 1 | 5 | 5 | Low | 2026-11-25 | Open
RA-011 | Production Availability | Compute, networking and managed services | Service availability | Cloud outage or capacity issue causes prolonged customer disruption | Provider outage / capacity failure | CP-2, CP-10, SC-5, SC-6 | 3 | 4 | 12 | Medium | Availability monitoring, capacity thresholds, redundancy, tested recovery procedures | Infrastructure | Reduce | 2 | 4 | 8 | Medium | 2027-01-15 | Open
RA-012 | Data Retention | Customer data stores and backups | Personal and business data | Data retained longer than necessary increases breach impact and compliance exposure | Process failure / configuration drift | SI-12, MP-6, SC-28 | 3 | 4 | 12 | Medium | Retention schedule, automated deletion, backup lifecycle controls, quarterly validation | Data Governance / GRC | Reduce | 1 | 4 | 4 | Low | 2026-12-30 | Open

## Scoring Method
Likelihood | Definition
1 | Rare – unlikely under current conditions
2 | Unlikely – possible but not expected
3 | Possible – credible scenario
4 | Likely – expected to occur periodically
5 | Almost Certain – frequent or highly probable
Impact | Definition
1 | Negligible – minimal operational/security effect
2 | Minor – limited disruption or exposure
3 | Moderate – material business or security impact
4 | Major – significant customer, legal, financial or operational impact
5 | Severe – critical business impact or major data/security compromise
Score | Rating
1-4 | Low
5-9 | Medium
10-15 | High
16-25 | Critical